## MDR JAI
ENGINEERING DEPARTMENT
DRAWING CONTROL - MASTER DRAWING REGISTER
Prepared |  | : | Hilda | [37 empty] | Start |  | Start | : 29 Agustus 2018
Checked |  | : | Didi Kardiyono | [37 empty] | Update |  | Update | : 10 Oktober 2018
Hull Number |  | : | TB.101, TB.102, TB.103, TB.105
Type |  | : | Harbour Tug (2x2200 HP)
Main Dimension |  | : | 32 X 11.6 X 5.1 Meter
No. Kontrak |  | :
Owner |  | : | Jasa Armada Indonesia (JAI)
No. | Drawing Tittle / Description | Drawing No. |  | Revision Drawing |  |  | Latest Drawing Status from BKI | [13 empty] | Drawing to OS for Review |  |  |  |  | Drawing for Dept. OWNER | [5 empty] | Drawing for Dept. PROJECT | [5 empty] | Drawing for Dept. QC | [5 empty] | Remarks
|  |  |  | 0 | 1 | 2 | IFR | IFA | IFC | Sent to Class |  |  | Received fr Class |  |  | Status* |  |  | Comment Class BKI | Remarks | Revision |  |  |  | Comment OS | Revision | [5 empty] | Revision | [5 empty] | Revision
[21 empty] | 0 | 1 |  | 2 |  | 0 | 1 | 2 | 3 | 4 | 5 | 0 | 1 | 2 | 3 | 4 | 5 | 0 | 1 | 2 | 3 | 4 | 5
|  | Citra Shipyard | Designer | [17 empty] | Issue Date | Issue Date | Issue Date | Issue Date |  | Issue Date | Issue Date | Issue Date | Issue Date | Issue Date | Issue Date | Issue Date | Issue Date | Issue Date | Issue Date | Issue Date | Issue Date | Issue Date | Issue Date | Issue Date | Issue Date | Issue Date | Issue Date
[10 empty] | R.0 | R.1 | R.2 | R.0 | R.1 | R.2 | R.0 | R.1 | R.2
BASIC DRAWING
1 | General Arrangement |  | B-11-102 |  |  |  |  | √ |  | R.0: 29/08/2018; R.0: 28/09/2018; R.0: Diketahui
2 | Dimensional Profile |  | B-11-103 |  |  |  |  | √
3 | Lines Plan |  | B-21-101 |  |  |  |  | √ |  | R.0: 15/09/2018; R.0: 28/09/2018
4 | Offset Table |  | B-21-102 |  |  |  |  | √
5 | Inclining Test Procedure & Record |  | T-31-001 |  |  |  |  | √
6 | Hydrostatic Table |  | B-31-101 |  |  |  |  | √
7 | Cross Curve of Stability |  | B-31-102 |  |  |  |  | √
8 | Capacity Plan |  | B-31-103 |  |  |  |  | √
9 | Sounding Table |  | B-31-104 |  |  |  |  | √
10 | LWT & Weight Distribution Report |  | B-31-105 |  |  |  |  | √
11 | Tonnage Calculation |  | B-31-106 |  |  |  |  | √
12 | Freeboard Calculation |  | B-31-107 |  |  |  |  | √
13 | Preliminary Trim & Stability Calculation |  | B-31-108 |  |  |  |  | √
14 | Lightship Survey Calculation |  | B-31-109 |  |  |  |  | √
15 | Bonjean Table |  | B-31-110 |  |  |  |  | √
16 | Bollard Pull Calculation |  | B-31-111 |  |  |  |  | √
17 | Speed & Power Prediction |  | B-31-112 |  |  |  |  | √
HULL CONSTRUCTION
1 | Midship Section |  | H-12-002 |  |  |  |  | √ |  | R.0: 29/08/2018; R.0: 28/09/2018; R.0: Disetujui
2 | Profile & Deck Plan |  | H-22-001 |  |  |  |  | √ |  | R.0: 29/08/2018; R.0: 28/09/2018; R.0: Disetujui
3 | Shell Expantion |  | H-22-002 |  |  |  |  | √ |  | R.0: 29/08/2018; R.0: 28/09/2018; R.0: Disetujui
4 | Welding Table |  | H-22-003 |  |  |  |  | √ |  | R.0: 29/08/2018; R.0: 28/09/2018; R.0: Disetujui
5 | Welding Detail & Procedure |  | H-22-004 |  |  |  |  | √ |  | R.0: 29/08/2018; R.0: 28/09/2018; R.0: Diketahui
6 | Trans Section And Bulkhead |  | H-22-005 |  |  |  |  | √ |  | R.0: 2018-10-09; R.0: 28/09/2018; R.0: Disetujui
7 | Docking Plan |  | H-22-006 |  |  |  |  | √ |  | R.0: 2018-09-10
8 | Material Estimation |  | H-22-007 | [5 empty] | √
9 | Engine Girder & Foundation |  | H-32-003 |  |  |  |  | √ |  | R.0: 2018-09-10
10 | Sea Chest Construction |  | H-32-004 |  |  |  |  | √ |  | R.0: 2018-09-10
11 | Superstructure Construction |  | H-32-005 |  |  |  |  | √ |  | R.0: 2018-10-09; R.0: 28/09/2018; R.0: Disetujui
12 | Z Drive Seating Construction |  | H-32-006 |  |  |  |  | √
13 | Skeg Construction |  | H-32-007 |  |  |  |  | √ |  | R.0: 20/09/2018; R.0: 28/09/2018; R.0: Disetujui
14 | Funnel Contruction |  | H-32-008 |  |  |  |  | √ |  | R.0: 2018-09-10
15 | Hawse pipe & Anchor Pocket Contruction |  | H-22-009 |  |  |  |  | √
16 | Towing Hook & Deck Machinary Seating Reinforcement |  | H-32-010 |  |  |  |  | √
17 | Bulwark Construction |  | H-32-011 |  |  |  |  | √
18 | X- RAY PLAN |  | H-32-012 |  |  |  |  | √ |  | R.0: 2018-09-10
19 | Main Genset Foundation |  | H-32-013 |  |  |  |  | √
20 | Scantling Calculation |  | H-11-001 |  |  |  |  | √ |  | R.0: 20/09/2018; R.0: 28/09/2018; R.0: Referensi
HULL OUTFITTING
1 | Equipment Number |  | O-11-101 |  |  |  |  | √ |  | R.0: 29/08/2018; R.0: 28/09/2018; R.0: Referensi
2 | Mooring & Towing Arrangement |  | O-32-102 |  |  |  |  | √ |  | R.0: 15/09/2018; R.0: 28/09/2018; R.0: Diketahui
3 | Fire Protection |  | O-22-203 |  |  |  |  | √
4 | Fire Fighting & Safety Plan |  | O-22-204 |  |  |  |  | √
5 | Accomodation Arrangement |  | O-22-305 | [5 empty] | √
6 | Door & Window Arr'nt |  | O-22-306 |  |  |  |  | √
7 | Manhole Arrangement |  | O-32-107 |  |  |  |  | √
8 | Hatch Arrangement & Detail |  | O-32-108 | [5 empty] | √
9 | Vertical Ladder (Outside & Inside) |  | O-32-109 | [5 empty] | √
10 | Inclined Ladder ( Outside & Inside) |  | O-32-110 | [5 empty] | √
11 | Hawse Pipe & Anchor Pocket Arrangement |  | O-32-111 | [5 empty] | √
12 | Towing Hook Arrangement |  | O-32-112 |  |  |  |  | √
13 | Towing Staple Arrangement & Detail |  | O-32-113 |  |  |  |  | √
14 | Bollard Details |  | O-32-114 |  |  |  |  | √
15 | Towing Winch Windlass Foundation |  | O-32-115 |  |  |  |  | √
16 | Radar Mast Detail |  | O-32-116 | [5 empty] | √
17 | Independent Tank |  | O-32-117 | [5 empty] | √
18 | Thruster Compartment Opening Cover |  | O-32-118 |  |  |  |  | √
19 | Railing Arrangement |  | O-32-115 |  |  |  |  | √
20 | Hand & Storm Rail |  | O-32-104 | [5 empty] | √
21 | Cathodic Protection Arr'nt & Calculation |  | O-22-402
22 | Rubber Fender Arr |  | O-32-122 |  |  |  |  | √
23 | Tyre Fender Arrangement |  | O-32-123 | [5 empty] | √
24 | Draft Mark & Freboard Mark Arr'nt |  | O-32-124 |  |  |  |  | √
25 | Plummer Block Seating |  | O-32-125 |  |  |  |  | √
26 | Sea Chest Grating Detail |  | O-32-126 | [5 empty] | √
27 | Engine Room Lifting Beam Arrangement |  | O-32-127 | [5 empty] | √
28 | Bottom Plug Arrangement |  | O-32-128 | [5 empty] | √
29 | Arrangement Liferaft & Seating |  | O-32-129 | [5 empty] | √
30 | Galley Arrangement |  | O-32-130 | [5 empty] | √
31 | Wheel House Arrangement |  | O-32-131 | [5 empty] | √
32 | In Water Mark Plan |  | O-32-132 |  |  |  |  | √
33 | Echo Sounder & Speed Log Arrangement |  | O-32-133 | [5 empty] | √
34 | Engine Room Louvre |  | O-32-134 | [5 empty] | √
35 | Ship Name Arrangement |  | O-32-135 | [5 empty] | √
36 | Funnel Mark |  | O-32-136 | [5 empty] | √
37 | Fifi Monitor Foundation |  | O-32-137 | [5 empty] | √
38 | Machinery Room Flooring Arrangement |  | O-32-138 | [5 empty] | √
39 | Chain Locker Arrangement |  | O-32-139 | [5 empty] | √
MACHINERY & PIPING SYSTEM
1 | Bilge, Ballast & Fire System |  | M-22-101 |  |  |  |  | √ |  | R.0: 2018-04-10
2 | Ext. Fire Fighting & Deluge System |  | M-22-102 |  |  |  |  | √
3 | Compressed Air System |  | M-22-103 |  |  |  |  | √
4 | Sounding Air Pipe |  | M-22-104 |  |  |  |  | √
5 | Fuel Oil System |  | M-22-105 |  |  |  |  | √
6 | Cooling System |  | M-22-106 |  |  |  |  | √
7 | Lubrication Oil System |  | M-22-107 |  |  |  |  | √
8 | Outside Deck Scupper System |  | M-22-108 |  |  |  |  | √
9 | FW And SW Sanitary System |  | M-22-109 |  |  |  |  | √
10 | Exhaust Gas Piping System |  | M-22-110 |  |  |  |  | √
11 | Drainage, Soil & Sanitary System |  | M-22-111 |  |  |  |  | √
12 | Dirty Oil System |  | M-22-112 |  |  |  |  | √
13 | Oil Dispersant System |  | M-22-113 |  |  |  |  | √
14 | Engine Room Lay Out |  | M-23-301 |  |  |  |  | √
15 | Shafting Arrangement |  | M-23-205 |  |  |  |  | √
ELECTRIC OUTFITTING
1 | Electrical Power Consumption Table |  | E-11-101 |  |  |  |  | √
2 | Batteray Calculation |  | E-11-102 |  |  |  |  | √
3 | Short Circuit Calculation |  | E-11-104 |  |  |  |  | √
4 | General Electric Diagram |  | E-22-201 |  |  |  |  | √
5 | Arrangement of Electrical Equipment |  | E-33-101 |  |  |  |  | √
6 | Navigation Light Arrangement |  | E-33-201 | [5 empty] | √
7 | Arrangement Main Cable Way |  | E-33-301 |  |  |  |  | √
8 | Arrangement of DB and Starter Panel |  | E-33-303 | [5 empty] | √
9 | PA, Fire Alarm & General Alarm System |  | E-33-402 | [5 empty] | √
10 | Arrangement of Tank Level Alarm |  | E-33-205
CARPENTRY & HVAC
1 | Insulation Plan & Detail |  | Dcp/18/01
2 | Wall Panelling Layout |  | Dcp/18/01
3 | Deck Covering Plan & Detail |  | Dcp/18/01
Production Drawing
NESTING & ASSEMBLY DRAWING
1 | Block 1
| Assembly Drawing |  | P-14-01A | [5 empty] | √
| Assembly Part List |  | P-14-01C | [5 empty] | √
| Nesting Plate |  | P-14-01E | [5 empty] | √
| Profile Sketch |  | P-14-01F | [5 empty] | √
| Cutting Plan Profile |  | P-14-01G | [5 empty] | √
| Bending Info |  | P-14-01H | [5 empty] | √
| List Material |  | P-14-01I | [5 empty] | √
2 | Block 2
| Assembly Drawing |  | P-12-01A | [5 empty] | √
| Assembly Part List |  | P-12-01C | [5 empty] | √
| Nesting Plate |  | P-12-01E | [5 empty] | √
| Profile Sketch |  | P-12-01F | [5 empty] | √
| Cutting Plan Profile |  | P-12-01G | [5 empty] | √
| Bending Info |  | P-12-01H | [5 empty] | √
| List Material |  | P-12-01I | [5 empty] | √
3 | Block 3
| Assembly Drawing |  | P-13-01A | [5 empty] | √
| Assembly Part List |  | P-13-01C | [5 empty] | √
| Nesting Plate |  | P-13-01E | [5 empty] | √
| Profile Sketch |  | P-13-01F | [5 empty] | √
| Cutting Plan Profile |  | P-13-01G | [5 empty] | √
| Bending Info |  | P-13-01H | [5 empty] | √
| List Material |  | P-13-01I | [5 empty] | √
4 | Block 4
| Assembly Drawing |  | P-13-02A | [5 empty] | √
| Assembly Part List |  | P-13-02C | [5 empty] | √
| Nesting Plate |  | P-13-02E | [5 empty] | √
| Profile Sketch |  | P-13-02F | [5 empty] | √
| Cutting Plan Profile |  | P-13-02G | [5 empty] | √
| Bending Info |  | P-13-02H | [5 empty] | √
| List Material |  | P-13-02I | [5 empty] | √
5 | Block 5
| Assembly Drawing |  | P-15-01A | [5 empty] | √
| Assembly Part List |  | P-15-01C | [5 empty] | √
| Nesting Plate |  | P-15-01E | [5 empty] | √
| Profile Sketch |  | P-15-01F | [5 empty] | √
| Cutting Plan Profile |  | P-15-01G | [5 empty] | √
| Bending Info |  | P-15-01H | [5 empty] | √
| List Material |  | P-15-01I | [5 empty] | √
6 | Block 6
| Assembly Drawing |  | P-15-02A | [5 empty] | √
| Assembly Part List |  | P-15-02C | [5 empty] | √
| Nesting Plate |  | P-15-02E | [5 empty] | √
| Profile Sketch |  | P-15-02F | [5 empty] | √
| Cutting Plan Profile |  | P-15-02G | [5 empty] | √
| Bending Info |  | P-15-02H | [5 empty] | √
| List Material |  | P-15-02I | [5 empty] | √
7 | Block 7
| Assembly Drawing |  | P-12-02A | [5 empty] | √
| Assembly Part List |  | P-12-02C | [5 empty] | √
| Nesting Plate |  | P-12-02E | [5 empty] | √
| Profile Sketch |  | P-12-02F | [5 empty] | √
| Cutting Plan Profile |  | P-12-02G | [5 empty] | √
| Bending Info |  | P-12-02H | [5 empty] | √
| List Material |  | P-12-02I | [5 empty] | √
SYSTEM AND OUTFITTING PRODUCTION DRAWING
1 | Sea Chest Cross Over Pipe |  | P-23-101 | [5 empty] | √
2 | Tank Penetration |  | P-23-102 | [5 empty] | √
3 | Bilge, Ballast & Fire Arr & Spool Details |  | P-23-103 | [5 empty] | √
4 | Air Vent, Sounding & Filling Piping System |  | P-23-104 | [5 empty] | √
5 | Cooling Arr & Spool Details |  | P-23-105 | [5 empty] | √
6 | Outside Deck Scupper System |  | P-23-106 | [5 empty] | √
7 | Arrangement Of Overboard Pipe |  | P-23-107 | [5 empty] | √
8 | Engine Exhaust Gas Piping Arr & Spool Details |  | P-23-108 | [5 empty] | √
9 | Ducting in Machinery Room |  | P-23-109 | [5 empty] | √
10 | Cable Way in Machinery Room |  | P--23-110 | [5 empty] | √
11 | Ext. Fire Fighting & Deluge Arr & Spool Details |  | P-23-011 | [5 empty] | √
12 | Fire Main & Deckwash System |  | P-23-112 | [5 empty] | √
13 | Soil & Drain Pipes |  | P-23-113 | [5 empty] | √
14 | Domestic F.W./S.W. Supply System Below Main Deck |  | P--23-114 | [5 empty] | √
15 | Oil Dispersant Arr & Spool Details |  | P-23-015 | [5 empty] | √
16 | Dirty Oil Arr & Spool Details |  | P-23-016 | [5 empty] | √
17 | Fuel Oil Arr & Spool Details |  | P-23-017 | [5 empty] | √
18 | Lubrication Oil Arr & Spool Details |  | P-23-018 | [5 empty] | √
19 | Compressed Air Arr & Spool Details |  | P-23-019 | [5 empty] | √
20 | Ducting in Accomodation Space |  | P-23-020 | [5 empty] | √
21 | Cable Way in Accomodation Space |  | P-23-021 | [5 empty] | √
22 | CO2 System |  | P-23-022 | [5 empty] | √
23 | Domestic F.W./S.W. Supply System Above Main Deck |  | P-23-023 | [5 empty] | √
24 | Coordination Drawing on Funnel |  | P-23-024 | [5 empty] | √
25 | Coordination Drawing on Engine Room |  | P-23-025 | [5 empty] | √
26 | Coordination Drawing on Accomodation |  | P-23-026 | [5 empty] | √
EQUIPMENT SEATING
1 | Harbour Genset Seating |  | S-23-101 | [5 empty] | √
2 | Bilge Pump Seating |  | S-23-102 | [5 empty] | √
3 | Ballast/GS Pump Seating |  | S-23-103 | [5 empty] | √
4 | M/E Lub. Oil STBY Seating |  | S-23-104 | [5 empty] | √
5 | STBY FW Cooling Pump Seating |  | S-23-105 | [5 empty] | √
6 | STBY SW Cooling Pump Seating |  | S-23-106 | [5 empty] | √
7 | M/E FW Cooler Seating |  | S-23-107 | [5 empty] | √
8 | M/E LO Cooler Seating |  | S-23-108 | [5 empty] | √
9 | Starting Air Compressor Seating |  | S-23-109 | [5 empty] | √
10 | Emergency Air Compressor Seating |  | S-23-110 | [5 empty] | √
11 | Starting Air Reservoir Seating |  | S-23-111 | [5 empty] | √
12 | FO Transfer Pump Seating |  | S-23-112 | [5 empty] | √
13 | FO Purifier Seating |  | S-23-113 | [5 empty] | √
14 | LO Purifier Seating |  | S-23-114 | [5 empty] | √
15 | Sewage Treatment Plant Seating |  | S-23-115 | [5 empty] | √
16 | Sewage Pump Seating |  | S-23-116 | [5 empty] | √
17 | FW Hydrophore Seating |  | S-23-117 | [5 empty] | √
18 | SW Hydrophore Seating |  | S-23-118 | [5 empty] | √
19 | Oily Water Separator Seating |  | S-23-119 | [5 empty] | √
20 | Sludge/ Dirty Oil Pump Seating |  | S-23-120 | [5 empty] | √
21 | SW Cooling Pump for AHU Seating |  | S-23-121 | [5 empty] | √
22 | Anchor Windlass Power Pack Seating |  | S-23-122 | [5 empty] | √
23 | External Fifi Pump Seating |  | S-23-123 | [5 empty] | √
24 | Oil Dispersant Pump Seating |  | S-23-124 | [5 empty] | √
25 | Foam Pump Seating |  | S-23-125 | [5 empty] | √
Note on AM67: ENGINEERING: Approved drawing tagl 15/08/2018